## Pour
Concrete Pour Checklist
The truck does not wait.
Pour |  | Date
Everything here has to be done before the truck arrives, because none of it can be done while it is there. Tick as you go and keep the sheet — the batch log at the bottom is worth having if anything goes wrong later.
A week before
Task | Done | Date | Notes
Volume worked out and 5 to 10% added — running short mid-pour is unrecoverable
Mix, slump and any fiber or additive agreed with the supplier
Access checked: can the truck reach, and how far will the chute actually go?
Enough people lined up. A pour is not a one-person job at any size.
The day before
Task | Done | Date | Notes
Forms braced, square and level — checked again, not remembered from yesterday
Rebar or mesh in place, tied, and held up off the base on chairs
Base compacted and damp, not dry and not flooded
Weather checked: not freezing tonight, not over 90°F tomorrow, no rain during the pour
Tools out and clean: screed, bull float, edger, groover, hose, buckets, boots
On the day, before the chute swings
Task | Done | Date | Notes
Ticket checked: volume, mix and time batched all match what you ordered
Someone on the screed, someone moving concrete, someone on the hose
Where the wash-out goes — decided now, not when the driver asks
After the truck leaves
Task | Done | Date | Notes
Bleed water gone before floating. Working it while wet weakens the surface.
Control joints cut or tooled within the first day, a quarter of the slab depth deep
Covered and kept damp for seven days — plastic, wet burlap or a curing compound
Forms left on for at least two days, longer in cold weather
No foot traffic for 24 hours, nothing heavy for a week, no vehicles for 28 days
Ticked so far | 0 |  | of 17 tasks
What went in
Ticket no. | Time batched | Volume (cu yd) | Mix / slump
Concrete pour checklist · free from onetripdiy.com/printables/