## Sequence
Renovation Sequence Checklist
Each stage tells you what the next one can order.
Room |  |  | Start
Shaded cells are the ones you fill in. Everything else calculates itself — row 9 is an example, type over it or delete it. Tick the Done column and the progress line counts it.
# | Stage | What it lets you order next | Done | Date | Notes
1 | Strip out | Nothing yet — you are finding out what is really there
2 | Structural and openings | Framing lumber, headers, beams
3 | Rough plumbing and electrical | Nothing finish-related until this is inspected
4 | Insulation | Bags or rolls, from wall and ceiling area
5 | Drywall | Sheets, screws, tape and compound
6 | Prime and first coat | Paint, from wall area — ceiling separately
7 | Flooring | Boxes and underlayment, over a clean level substrate
8 | Trim and baseboard | Linear feet from the perimeter, less door openings
9 | Final coat and touch-up | The last gallon, and the record card
10 | Fixtures and fittings | Everything that was waiting on a finished surface
| Stages done |  | 0 |  | of 10
Notes — what you found behind the wall
• Buying ahead of an unknown is guessing. The wall has to be open before some of this is real.
• Rough inspections gate everything after them. Book early; they are rarely same-week.
• Finished floor height decides trim, door clearance and thresholds. Fix it before you order.
Renovation sequence checklist · free from onetripdiy.com/printables/